## Slide 1: Lead Technology KPIs: Executive Summary (1/2)
Service Availability & Major Incidents
NW & IT projects execution
Describe RAN, Tx, Fiber and IT projects rollout progress (explain delays/challenges versus plan or ahead of plans) and Impact in Tech Capex/Tech Opex versus budgets.
OML purchased 500 batteries, Batch-1(246 units) had arrived on 29th Jan 2024 and remaining (254 units) arrived on 14th Feb 2024. All 130 sites had been installed the batteries and a termination notice had been sent to EDOTCO. 67 sites already started in-house on 1st April and the following 63 will be on 6th Sep 2024. Another batch 503 sites will be effective on 22nd Sep 2024 as well.
Network Critical outage continue especially Rakhine, Sagaing, Kachin & Kayin due to linear fiber cuts whereas protections paths are not recoverable. Access restriction and fuel delivery restriction is still challenging in Rakhine, Kayin & Kachin (Putao) region. RAW3043+33 sites are still down due to fiber issue between RAW3082 & RAW3035 since 10th Jan 2023 due to Fiber cut and War zone area.
Mandalay ISP path is also on risk due to wildfire issue at the Tachileik border, frequents fiber cut issues had happened due to the wildfire however swapped with MFOCN fiber at frequent cut section to prevent MDY ISP linear. 60% progress had been done and target to finish by the end of May.
Yangon ISP path is down due to Eager DWDM link between KNW6032-KNW6041 was down since 23rd Nov 2023 in the conflict area and protection MFOCN link is down between kNW6029 and KNW6041 on 2nd April 2024 due to ongoing conflict and war. Eager and MFOCN teams keep trying for access with Military in Kawkareik township for KNW6032 fiber cut. As a mitigation plan, Campana Submarine 100G had been activated on 25th April 2024.
KCW0092+219 impacted both voice and data outage 3453 minutes total on 1st April, 9th April, 24th April and 30th April 2024 and 1st April 2024 due to 10G DPLC_Campana link down between MDL-DC-IPBB-18S-PE-02 (0/12/1/10) <> KCW0092 (0/7/0/4) CID: MMR-10G227.
Due to Nationwide grid system break down, 163 sites impacted on 17th April 2024, 518 site impacted on 20th April 2024 & 350 sites impacted on 30th April 2024.
(SAW0019+10 sites), Homalin data was impacted due to MFOCN fiber cut between SAW0019-SAW0297 on 13th April 2024 and team still cannot access due to landmine issue and military blocked the access route to the fault area.
Kayah sites were still down since 13th Nov 2023 due to war zone area.
Explain degradations/changes in availability trend, root cause and actions for improvement.
Describe major networks or IT outages/Incidents causing services disruptions, complaints or degradations in Voice/Data CSAT (if any)
TECH CAPEX:
Total CAPEX Spend YTD is 45.4% below budget. Delay on project delivery time in difference
TECH OPEX:
Tech OPEX YTD for NW is above budget YTD by 28.4% mainly due to Fuel rate increase by 34% (3,900Ks/ltr Vs 2,916Ks/ltr) and FX impact (3,073//2,616).•Tech OPEX YTD for IT is below budget YTD by 3.1%.
Tx, FIBER NW and/or FTTX/FWA Projects:
100G DWDM link set up with HTI (B2B) was done.
10G PNI with Zenlayer was done, to improve user experience.
40G Metro Ring over DWDM between Thaton and Mawlamyaing was done to solve high utilization.
New SSU cards I&C is ongoing for synchronization modernization. Estimated to be done by Q2_2024.
Planned to restore the Cesium Clock faulty in YGN and MDY DC. Estimated to be done by Q2_2024.
Firewall Modernization is ongoing , estimated to be done by end of April,_2024.
Additional fiber adding in TCL ISP Path is ongoing , to be done by Q2-2024.
100G DWDM/ IPBB Expansion is ongoing, to be done b y Q2-2024.
100G Expansion along MDY-TCL ISP path is ongoing, to be done by Q2-2024.
10G Card Expansion for IP Metro Network is ongoing , to be done by Q3, 2024.
RAN Projects:
• Number of cumulative YTD RAN physical sites integrated = 5836
Total new sites planned for 2023 = 9
  3/9 : On air (BAW5666 – 08 June, SAW0771 – 29 Sep, KCW0370 – 29 Dec)
  6/9 : TC approved on 24 Aug. PO released 22 Sep. Delayed as currently in unsafe area
Total new sites planned for 2024 = 40
  15 sites : 3/15 – TC approved & PO released, 12/15 sites : Business case preparation ongoing
  3 sites :
    Yoma bank (B2B request). Solution confirmed by customer. TSSR completed. Target May 2024
    Golden city (VIP complaint) : TSSR completed. Leasing contract ongoing. Target May 2024
    Sky suite (VIP complaint) : Negotiation ongoing. Target May 2024
• Capacity expansions
Layer upgrade existing sites – Equipment Reuse : 127 completed. 21 planned
Batch 4 : 51/55 completed, 04/55 pending. Delay to due volatile safety situation. Target : TBD depending on site access
Batch 6 : 33/50 completed, 17/51 pending. Equipment will be reuse from data lock sites as per OG instructions (dismantle from data lock sites and install in congested sites.
Target May 2024 (depending on site access)
Dismantle activity : Batch 1 - 22/50 sites completed. Rest on hold due to safety issues.
Batch 2 (L1800 RRU recovery only) : 10 sites PO released. Activity will start Wk19
Layer upgrade existing sites – New equipment ordering : 50 sites CVD & TC approved. PO released
HOS existing sites – New equipment ordering : [1] 8 HOS sectors CVD & TC approved. PO released.
: [2] 20 HOS sectors OG & TC approved. PO released
• IBS reactivation :
Batch – 1 : 10 locations planned - 10/10 sites on air - Closed
Batch – 2 : 08 locations planned - 3/8 site on air, 2/8 WIP, 1/8 TC on week19. 2/8 under negotiation by sourcing.
• Nokia RAN software upgrade
4G Megaplexer migration completed (3/3)
RNC software upgrade (20C22R3) : Total 3/5 completed. 2/5 planned. Target May 2024.
SBTS software upgrade (21B22R3) : Planned after RNC software upgrade. Target May 2024
• POC power comparison (ZTE vs Nokia)
Type 3B (like to like) : 1/2 sites rollback completed to bare minimum Nokia configuration. Power consumption increased by ~28% in Nokia as compared to ZTE - Closed
Type 1 (like to like) : 2/2 sites completed. Power consumption reduced by ~21% in ZTE as compared to Nokia - Closed
TT ID | Fault First Occur Time | Fault Recovery Time | Outage Minutes | Hub Site ID | Down Site Count | Bucket | RCA | Mitigation Plan | TT Status
TT202404201824 | 4/20/2024 13:12 | 4/21/2024 9:10 | 1198 | YAW4382 | 518 |  | Nation Wide Grid failed | National Grid. | Closed
TT202404301439 | 4/30/2024 9:04 | 5/1/2024 9:06 | 1442 | Multi Hub | 220 | Campana | Site was down due to fiber issue. Observing 10G DPLC_Campana link down between MDL-DC-IPBB-18S-PE-02 (0/12/1/10) <> KCW0092 (0/7/0/4) CID: MMR-10G227 and protection link down , Observing OML-Eager Link down between SAW0307(80km) To MAW2243(80km) at 2024-04-25 09:02:27 . After link restored(10G DPLC_Campana link restored between MDL-DC-IPBB-18S-PE-02 (0/12/1/10) <> KCW0092 (0/7/0/4) CID: MMR-10G227 and protection link restored) , site got restored. | _As last couple months status, Fiber Supplier can't support our fiber demands for MKN protection due to ground situations. | Closed
 |  |  |  |  |  |  |  | _We have released WO to install protection link between SAW0307(80km) To MAW2243(80km), installation is pending because of power issue. | 
TT202404011533 | 4/1/2024 14:22 | 4/2/2024 15:45 | 1523 | KCW0092 | 184 | Campana | Site was down due to fiber issue. Observing 10G DPLC_Campana link down between MDL-DC-IPBB-18S-PE-02 (0/12/1/10) To KCW0092 (0/7/0/4) CID: MMR-10G227 and Protection link Optima sharing TML-MGT link down between SAW0087(80km) To SAW0498(80km) at 2024-03-31 16:55:12.Site got restored after 10G DPLC_Campana link Up between MDL-DC-IPBB-18S-PE-02 (0/12/1/10) To KCW0092 (0/7/0/4) CID: MMR-10G227 .Awaiting root cause from Global-Net Team. Sites restored SAW0087 and SAW0498 link restored | _As last couple months status, Fiber Supplier can't support our fiber demands for MKN protection due to ground situations. | Closed
 |  |  |  |  |  |  |  | _We have released WO to install protection link between SAW0307(80km) To MAW2243(80km), installation is pending because of power issue. | 
TT202404062029 | 4/6/2024 14:00 | 4/7/2024 10:42 | 1242 | SAW0273 | 78 | MFOCN/MGT | Site was down due to fiber issue. Sites are coming up after SAW0252-SAW0273 DWDM & IP link got restored .Awaiting detail RCA from fiber team | Already in ring | Closed
TT202404283585 | 4/28/2024 19:11 | 4/29/2024 8:07 | 776 | SAW0065 | 87 | MFOCN/FLM | Site was down due to fiber issue. Site was down due to DWDM Link fail between SAW0065 and SAW0273 & OVER_BRD_TMP at SAW0034 (Boards broken & Need spare).After team replaced it with a new DWDM card. Issue closed permanently. | Already in ring | Closed
TT202404230086 | 4/23/2024 0:16 | 4/24/2024 7:57 | 1901 | SHW1158 | 33 | Eager | SHW1094<>SHW1275 (20G),SHW1158<>SHW1978 (10G) P link down due to DWDM link fail between SHW1158 and SHW1094. Protection EAGER Fiber link down between SHW1275(80km) and SHW1195(80km) since 2024-04-20 11:55:27 due to SFNOCP faulty , Bend location 51.2 km from SH0168 (ATOM) (51.km from SHW1195) after fiber solving link still down and SFP faulty at SHW1275 and FSO team change new SFP | Already implemented new fiber with MFOCN. Released WO to ZTE to swap fiber from Eager to MFOCN | Closed
TT202404091433 | 4/9/2024 10:30 | 4/9/2024 16:45 | 376 | KCW0092 | 141 | Campana | Site was down due to fiber issue. Observing 10G DPLC_Campana link down between MDL-DC-IPBB-18S-PE-02 (0/12/1/10) To KCW0092 (0/7/0/4) CID: MMR-10G227.Sites got restored after 10G DPLC_Campana link restored between MDL-DC-IPBB-18S-PE-02 (0/12/1/10) To KCW0092 (0/7/0/4) CID: MMR-10G227 Awaiting detail RCA from Fiber team. | _As last couple months status, Fiber Supplier can't support our fiber demands for MKN protection due to ground situations. | Closed
 |  |  |  |  |  |  |  | _We have released WO to install protection link between SAW0307(80km) To MAW2243(80km), installation is pending because of power issue. | 
TT202404220939 | 4/22/2024 7:45 | 4/23/2024 16:31 | 1966 | MAW2116 | 25 | FLM | Observing OML-MGT fiber link down between MAW2113(80km) To MAW2119(80km), after link restored MAW2113-MAW2119 , 25 sites data services are restored | Ring already protected with MW | Closed
TT202404171471 | 4/17/2024 12:30 | 4/17/2024 16:59 | 270 | YAW4461 | 163 |  | Nation Wide Grid failed | National Grid. | Closed
TT202404060973 | 4/6/2024 8:33 | 4/7/2024 12:37 | 1684 | KCW0300 | 26 | MGT | Site was down due to fiber issue. Site got restored after KCW0300 - SAW0501 and SAW0501-SAW0372 fiber link restored. Awaiting detail RCA . | ring opened due to fiber prolong cut. Already issue PO to KNET for Mansi - Namhkam fiber implementation but can't continue due to ground situation. | Closed
TT202404131780 | 4/13/2024 12:57:34 PM | still down |  | SAW0019 | 10 | MFOCN | MFOCN fiber cut between SAW0019-SAW0297 and team still cannot access the fault area due to landmine and military blocked the access route. | ring was opened due to prolong fiber cut. | Open
CORE & IT/Digitalization Projects:
VoLTE Platform started FUT for selected users. Under profiling for go launch plan.
vDC setup completed for new Enterprise market. Now doing POC for vDC solution with open-stacks solution.
OML inhouse software developments delivered 60% of the total business Change requests and configuration change request via inhouse team in Jan.
In-house Subscription loan project is completed and UAT completed. Awaiting business green-light.
No critical/major incident.
Notes: Option B: Split into two slides

## Slide 2: Lead Technology KPIs: Executive Summary (2/2)
Voice Performance
Data Performance
Describe degradations/changes in voice performance (Accessibility, Congestion, Drop, audio quality)
Describe degradations/changes in Data performance (Accessibility, Congestion, Drop, Tutela ECQ/CCQ)
Explain changes in Voice traffic and Data volume trends (% growth/decrement and reasons), tendencies per technology and seasonality effects
Traffic trends:
Access Monthly Technology KPIs using the link below:
https://app.powerbi.com/links/4AI7J6Q0Fn?ctid=35ce61ea-2a69-4c72-837c-f38de143a7a3&pbi_source=linkShare
Voice:
Voice traffic degraded to -2%.
Data:
There is a 4.1% Incremented in data traffic compared to day on day of previous month, Observed 3G+4G Traffic played major hike compared to Mar month.
2G:
2G CSSR is majorly impacted for BSC104 due to ongoing incidents in Rakhine area and 4 sites working on VSAT are having very high congestion in both RAN & TX.
Also 2G CSSR is normally low due to data lock region top failure sites having high congestion due to capacity limitation and coverage issue due to high inter site distance & Prolong site down issue cause non continues coverage.
Working on top cell analysis and action plan on daily basic to improve the CSSR % & raise the other domain related issue on time with WO.
TCH Congestion cells increased mainly due to Nation wide grid failures started from Feb-24 and continuous outages increased in all the regions since 19-Mar.
Also there is traffic growth in most of the areas of Sagaing that lead to more congestion cells . Whereas overall NW availability is also impacted. Actions are ongoing for data lock/high congestion regions for congestion mitigation.
TCH drop started increasing since Apr-23 with increase in 900 Band interference across NW and got worst in Jul-23 and continuously increasing.
3G:
3G CSSR is majorly impacted with high availability dip & Magway data lock sites & Rakhine area for having high congestion and fails as compared to last months.
Top failure sites having high congestion due to over occupied compare available capacity and coverage issue due to high inter site distance & Prolong site down issue cause non continues coverage.
CS RAB Congestion cells increased mainly due to Nation wide grid failure increased since last month.
VOLTE:
4G (In case of OP this is still 3G):
Increase in 900 Band interference across NW and got worst in Jul-23 and continuously increasing. In Sep-23, high interference cell count further increased
Also data volume is increasing in NW across all regions.
During water festival time traffic also increased, now coming back to normal trend.
5G:
Notes: Option B: Split into two slides